## Project_List
Region | CLUB | FMSS Location Number | FMSS Asset # | FMSS WO # | PST WO# | PMIS # | Component | ATC Project # | WORK TYPE | ASSET TYPE | DISTRICT | LOCATION | DEFICIENCY | Trail Assessment "AT ID" (indicate ID number, or range of IDs, project will address) | PROJECT DESCRIPTION | LIST ADDITIONAL MATERIALS AND/OR SERVICES NEEDED | ITEM | QTY | U.O.M | NPS Estimate | NPS Request Amount | ATC Direct Project | ATC Indirect (23.64%) | CREW | CREW WEEKS | YEAR | CLUB PRIORITY | FUND TYPE | NPS FUNDING Status | ENVIRO COMPLIANCE LEAD AGENCY? | PEPC # | PROJECT STATUS | CLUB ESTIMATE | Seg./Tract # | COMMENTS/OTHER: | LAST UPDATED | UPDATED BY: | CHANGES
2. MA | 1. NYNJTC | 77145 | 297371 | N/F | N/F | N/F |  |  |  | T | Orange-Rockland | Wildcat Shelter (284) | Wet area |  | Relocate side trail |  | Build/AddTrail: New -lf | 350 | LF |  |  |  |  | No Crew | 0 | 2013 | L |  |  | APPA |  | In Progress |  | 284 -01 |  | 2013-06-12 | JCB | Compliance is mostly complete; awating final signature
2. MA | 1. NYNJTC | 77145 | 297371 | N/F | N/F | N/F |  |  |  | T | Orange-Rockland | Little Dam Lake / E. Mombasha Rd (282) | Wet area |  | Relocate trail |  | Build/AddTrail: New -lf | 725 | LF |  |  |  |  | No Crew | 0 | 2013 | L |  |  | APPA |  | In Progress |  | 282-05 | Project proposal turned in to APPA | 2013-06-12 | JCB | Updated Status
2. MA | 1. NYNJTC | 81501 | 375124 | 9302337 | 9303420 | 188950 | A |  |  | OA | Orange-Rockland | Kloiber Field (283) | loss of valuable habitat |  | Mow field to maintain meadow. | [8 empty] | No Crew | 0 | 2013 | L |  |  | APPA |  | NEW PROJECT |  | 283-03 | Planning ongoing, club, ATC & APPA - more compliance? | 2013-06-12 | JCB | Updated Information and Comments
2. MA | 1. NYNJTC | 77145 | 297433 | 9346901 (NPS)/9346912 (Partner) | 9346924 | 191882 |  |  | DM | T | Orange-Rockland | Bear Mountain | [5 empty] | 150 | LF |  | 25000 | #REF! | #REF! | Mid-Atlantic | 5 | 2014 | H | CCSP | FUNDED - 2013 |  |  | NOT FUNDED |  |  | TA's not signed in time to fund 2013 BM Crew - carry forward to 2014 | 2013-06-12 | JCB | Updated Information and Comments
2. MA | 1. NYNJTC | 90545 | 363346 | 9318566 | 711943 | 190640 |  |  | CI | B | Orange-Rockland | Trout Brook (283-08) | Bridge is approaching the end of its life span. |  | Construct new 35-foot bridge. | Two telephone poles for the stringers. Fifty 2"x6"x12' CCA treated lumber. Thirty 2"x6"x12' CCA treated lumber. Fifteen pounds of 8d galvanized common nails. Other assorted hardware. | Build/AddLog Bridge -sf | 160 | SF | 13120 | 13120 | 20219.9935 | #REF! | Mid-Atlantic | 2 | 2015 | M | RR-T | Requested |  |  | Awaiting Funding | 2000 | 283-08 | WAS 2006 - move to 2015 | 2012-01-25 | JDR | REQUESTED (Bridge is in good shape. NO plans to do anything in immediate future.)
2. MA | 1. NYNJTC | [9 empty] | Orange-Rockland | Bear Mountain | Poor trail alignment- too steep, eroded |  | Continue work on BM AT Relo | [8 empty] | Mid-Atlantic |  | 2015 | H |  |  |  |  | NEW PROJECT |  |  |  | 2013-04-10 | BS | NEW PROJECT
2. MA | 1. NYNJTC | 77145 | 297433 | 712364 | 711342 | 191064 |  |  | CI | T | Orange-Rockland | Cascade Lake (285) | Illegal ATV use on A.T. lands. |  | Install boulder closures. | Contract services. | Build/Add: Gate-each | 5 | EA | 7234.5 | 6922 | 0 | 0 | No Crew | 0 | 2016 | H | RR-T | Requested |  |  |  | 10000 | 285 | Was PMIS 62416 (2006) | 2012-01-26 | JDR | REQUESTED
2. MA | 1. NYNJTC | [9 empty] | Orange-Rockland | Harriman SP | Dangerous crossing of Palisades Interstate Parkway |  | Find safer pedestrian crossing solution | BIG Bridge? | [7 empty] | No Crew |  | 2019 |  |  |  | PIPC? NY ORPHP? |  | NEW PROJECT |  |  |  | 2013-04-10 | BS | NEW PROJECT
Note on F1: Bundy, Jessica: Parent WO
Note on O1: "AT ID" is the unique ID number assigned to each deficiency found during the Trail Assessment. The "AT ID" can be found on the Google Earth Trail Assessment Disc provided to each club. The first letters of the AT ID indicate what type of deficiency: TR = Tread CS=Campsite SH=Shelter TO=Toilet (Privy) PK=Parking CR=Corridor BR=Bridge

## Completed_Projects
Region | CLUB | FMSS Asset Number | FMSS Equipment # | FMSS WO # | PST WO# | PMIS # | Component | ATC Project # | Work Type | ASSET TYPE | DISTRICT | LOCATION | DEFICIENCY | Trail Assessment "AT ID" (indicate ID number, or range of IDs, project will address) | PROJECT DESCRIPTION | LIST ADDITIONAL MATERIALS AND/OR SERVICES NEEDED | ITEM | QUANTITY | U.O.M | NPS Estimate | NPS Request Amount | ATC Direct Project | ATC Indirect (17.53%) | CREW? | CREW WEEKS | YEAR | Club Priority | Fund Type | NPS Funding Status | ENVIRO COMPLIANCE LEAD AGENCY? | PEPC # | Project Status | Club Estimate | Seg./Tract # | Comments/Other | Last Updated | Updated By | CHANGES
2. MA | 1. NYNJTC | 77145 |  | n/a |  |  |  | 2040 | Capital | T | Orange-Rockland | Bear Mountain (278-279) | This section of Trail is the most heavily used of the entire A.T. Thin soils, steep grade and extremely heavy use have resulted in severely eroded footpath that exceeds 30 feet in width for approximately 2 miles. |  | Relocate approximately 2 miles of the Trail. Construct 2 miles of stone crib wall and harden footpath. | One thousand tons of stone. One thousand tons of crushed fill. | Build/AddTrail: New -lf | 1000 | LF | NEED | 50000 |  |  | Mid-Atlantic | 10 | 2004 | H | RR-T |  |  |  | COMPLETE | $500K | 278-279 |  | 2007-02-19 | JDR | NO CHANGE
2. MA | 1. NYNJTC | 77145 | 297433 | 712365 |  | 108299 |  | FM-101 | Capital | T | Orange-Rockland | Bear Mountain (278-279) | This section of Trail is the most heavily used of the entire A.T. Thin soils, steep grade and extremely heavy use have resulted in severely eroded footpath that exceeds 30 feet in width for approximately 2 miles. |  | Relocate approximately 2 miles of the Trail. Construct 2 miles of stone crib wall and harden footpath. | One thousand tons of stone. One thousand tons of crushed fill. | Build/AddTrail: New -lf | 3400 | LF | 26010 | 26000 |  |  | Mid-Atlantic | 10 | 2005 | H | RR-S | Requested |  |  | COMPLETE | $500K | 278-279 |  | 2007-02-19 | JDR | NO CHANGE
2. MA | 1. NYNJTC | 77145 | 297433 | 712366 |  | 108299 |  | FM-101 | Capital | T | Orange-Rockland | Bear Mountain (278-279) | This section of Trail is the most heavily used of the entire A.T. Thin soils, steep grade and extremely heavy use have resulted in severely eroded footpath that exceeds 30 feet in width for approximately 2 miles. |  | Relocate approximately 2 miles of the Trail. Construct 2 miles of stone crib wall and harden footpath. | One thousand tons of stone. One thousand tons of crushed fill. | Build/AddTrail: New -lf | 1000 | LF | NEED | 156520 |  |  | Mid-Atlantic | 10 | 2006 | H | RR-S | Requested |  |  | COMPLETE | $500K | 278-279 |  | 2007-02-19 | JDR | COMPLETE
2. MA | 1. NYNJTC | 77145 | 297433 | 712367 |  | 108304 | A | FM-101 | Capital | T | Orange-Rockland | Bear Mountain (278-279) | This section of Trail is the most heavily used of the entire A.T. Thin soils, steep grade and extremely heavy use have resulted in severely eroded footpath that exceeds 30 feet in width for approximately 2 miles. |  | Relocate approximately 2 miles of the Trail. Construct 2 miles of stone crib wall and harden footpath. | One thousand tons of stone. One thousand tons of crushed fill. | Build/AddTrail: New -lf | 1000 | LF |  | 25000 |  |  | SCA | 4 | 2006 | H | PLC | Requested |  |  | COMPLETE | $500K | 278-279 |  | 2007-02-19 | JDR | COMPLETE
2. MA | 1. NYNJTC | 77145 | 297433 | 712368 |  | 108299 | C |  | Capital | T | Orange-Rockland | Bear Mountain (278-279) | This section of Trail is the most heavily used of the entire A.T. Thin soils, steep grade and extremely heavy use have resulted in severely eroded footpath that exceeds 30 feet in width for approximately 2 miles. |  | Relocate approximately 2 miles of the Trail. Construct 2 miles of stone crib wall and harden footpath. | One thousand tons of stone. One thousand tons of crushed fill. | Build/AddTrail: New -lf | 1000 | LF | NEED | 186616 |  |  | Mid-Atlantic | 10 | 2007 | H | RR-S | Requested |  |  | COMPLETE | $500K | 278-279 |  | 2009-01-21 | BS | Complete
2. MA | 1. NYNJTC | 77145 | 297433 | 713413 |  | 108304 | B |  | Capital | T | Orange-Rockland | Bear Mountain (278-279) | This section of Trail is the most heavily used of the entire A.T. Thin soils, steep grade and extremely heavy use have resulted in severely eroded footpath that exceeds 30 feet in width for approximately 2 miles. |  | Relocate approximately 2 miles of the Trail. Construct 2 miles of stone crib wall and harden footpath. | One thousand tons of stone. One thousand tons of crushed fill. | Build/AddTrail: New -lf | 1000 | LF | NEED | 25000 |  |  | SCA | 4 | 2007 | H | PLC | Requested |  |  | COMPLETE | $500K | 278-279 |  | 2009-01-21 | BS | Complete
2. MA | 1. NYNJTC | 77145 | 297433 | 893323 |  | 126228 | A | 2082 | Capital | T | Orange-Rockland | Bear Mountain (278-279) | This section of Trail is the most heavily used of the entire A.T. Thin soils, steep grade and extremely heavy use have resulted in severely eroded footpath that exceeds 30 feet in width for approximately 2 miles. |  | Relocate approximately 2 miles of the Trail. Construct 2 miles of stone crib wall and harden footpath. | One thousand tons of stone. One thousand tons of crushed fill. | Build/AddTrail: New -lf | 1000 | LF | NEED | 69015 | 58721.1776 | 10293.8224 | Mid-Atlantic | 10 | 2008 | H | RR-S | FUNDED |  |  | COMPLETE | $500K | 278-279 |  | 2009-01-21 | BS | Complete
2. MA | 1. NYNJTC | 77145 | 297433 | 712369 | 711325 | 126228 | B | 2082 | Capital | T | Orange-Rockland | Bear Mountain (278-279) | This section of Trail is the most heavily used of the entire A.T. Thin soils, steep grade and extremely heavy use have resulted in severely eroded footpath that exceeds 30 feet in width for approximately 2 miles. |  | Relocate approximately 2 miles of the Trail. Construct 2 miles of stone crib wall and harden footpath. | One thousand tons of stone. One thousand tons of crushed fill. | Build/AddTrail: New -lf | 1000 | LF | NEED | 169913.55 | 20219.9935 | 25000 | Mid-Atlantic | 10 | 2009 | H | RR-S | Requested | NY |  | COMPLETE | $500K | 278-279 | WAS PMIS # 117914 RR-T | 2009-02-04 | JDR | NO CHANGE
2. MA | 1. NYNJTC | 77145 |  | 3059343 | 3059462 | 154939 | A |  |  |  | Orange-Rockland | Bear Mountain (278-279) |  |  | This project will build upon the significant accomplishments of earlier trail rehabilitation projects in the Bear Mountain area of New York. This project constitutes the sixth phase of the project and involves the restoration of a section of approximately 1,000 linear feet of existing trail. A combination of volunteers and professionally led trail crews will complete the work. |  |  | 1000 | LF | 90000 | 90000 | 55819.3141 | 10293.8224 |  |  | 2010 | H | ARRA | FUNDED | NY State/ATPO | 26378 | COMPLETE |  |  |  | 2011-01-06 | JDR | ADDED for ARRA
2. MA | 1. NYNJTC | NEED | [6 empty] | Capital | B | Orange-Rockland | Little Dam Lake outlet (E. Mombasha Rd) (282) | Abutments have failed. Bridge structure is approaching the end of its life span. |  | Replace with step stones | [6 empty] | 137426.0353 | 149693.5565 | No Crew | 0 | 2010 | H |  |  |  |  | COMPLETE |  | 282-05 | May need to addresses sooner as safety issue: current bridge unlikely to last 7 years: 6x6 PT lumber abutments have failed, designing engineer suggests replacement of entire bridge | 2010-12-22 | BS | Completed by club
2. MA | 1. NYNJTC | 89654 | N/A | 896026 | 5095328 (PST WO may still need to be closed out) | 163981 | A |  | Demo | BU | Orange-Rockland | Fernau (284) | Incidentally acquired structures |  | Remove structure and restore tract to natural state. | Contract removal of structure | Structure | 1 | EA | 74881 | 74881 | #REF! | #REF! | No Crew | 0 | 2012 | H | RR-Demo | Requested | APPA |  | COMPLETE | 30000 | 284-? |  | 2011-01-06 | JDR | Move year
2. MA | 1. NYNJTC | 92059 | N/A | 893029 | 5095328 (PST WO may still need to be closed out) | 163981 | A |  | Demo | BU | Orange-Rockland | Baron (284-43) | Incidentally acquired structures |  | Remove structure and restore tract to natural state. | Contract removal of structure | Structure | 1 | EA | 39679 | 39679 | #NAME? | #NAME? | No Crew | 0 | 2012 | H | RR-Demo | Requested | APPA |  | COMPLETE | 30000 | 284-43 |  | 2011-01-06 | JDR | Move year
2. MA | 1. NYNJTC | 77145 | 297433 | 5098676 | 5104593 | 164045 | A |  | DM | T | Orange-Rockland | Fitzgerald Falls (283) | Trail to Falls not in optimal location; Trail along Falls eroded |  | Relocate Trail to Falls; install tread structures (steps, cribwall and landings) along Falls |  | Build/AddTrail: New -lf | 2500 | lf | 19125 | 9500 | 32092.3649 | #NAME? | Mid-Atlantic | 2 | 2013 | M | RR-T | FUNDED - 2013 |  |  | COMPLETE |  |  | Compliance done, Non-technical work between Trout Brook and falls done by club | 2013-06-12 | JCB | Changed to Completed
2. MA | 1. NYNJTC | 77154 | 297371 | 7897118 | N/F | N/F |  |  |  | T | Worthington State Forest | Yards Creek | Trail Relocation (flagged) |  | Relocate .75 mile of treadway |  | Build/AddTrail: New -lf | 3500 | LF |  |  | #NAME? | #NAME? | Mid-Atlantic | 0 | 2012 |  | RR-T | NEED | APPA | 25480 - need CE | COMPLETE |  |  | APPA ok'ed to proceed Fall 2011 | 2013-10-20 | JCB | Changed to COMPLETE
2. MA | 1. NYNJTC | 77154 | 297371 | 7897118 | N/F | N/F |  |  |  | T | Worthington State Forest | Yards Creek | Trail Relocation (flagged) |  | Relocate .75 mile of treadway |  | Build/AddTrail: New -lf | 3500 | LF |  |  | 32092.3649 | #NAME? | Mid-Atlantic | 0 | 2012 |  | RR-T | NEED | APPA | 25480 - need CE | COMPLETE |  |  | APPA ok'ed to proceed Fall 2011 | 2013-06-12 | JCB | Changed to Completed

## Instruction_Sheet
2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020
PAST YEAR(s) (requested in 2010) | CURRENT YEAR (requested in 2011) | OUT | Five Year Plan |  |  |  | NEW
|  | YEAR | (requested
|  | (requested in 2012) | in 2013)
Update Project Status | Confirm Projects | Review Projects | Review and Update | Adjust Project Scopes | Re-Arrange Projects | Remove Completed Projects | Add new Projects
Capital Planning
Five Steps: Fall 2013
The Capital Plan is designed to capture all of the A.T. project needs that may require National Park Service funding or projects that will take place on National Park Service lands and require environmental compliance.
1. Review past year projects (2013 and earlier) and indicate which ones have been completed, which ones need to be moved to another year because they were not done, or which ones can be removed from the list altogether. Once updated, the Plan should only contain projects for 2014 and beyond.
2. Review current year (2014) and next year (2015) projects to confirm scheduled work. Changes to the plan should be brought to the attention of the ATC regional staff as soon as possible so adjustments may be considered. No additional funding is available in these years. Any new or emergency project will need to replace or substitute an existing project on the list.
3. Review all other projects (2016 – 2019) on the list and make any necessary changes. When making changes, consider both the year planned and the scope of work.
4. Add new projects to 2020. 2020 is the only year for which new funding may be available; new projects should be listed here.
5. For each project, please indicate who the land owner is. It is particularly important to note any project that is wholly or partially located on NPS-APPA lands to aid in scheduling compliance reviews.
Use “Enviro Compliance Lead Agency” column to specify land/agency ownership.
6. Indicate the "AT ID" for each project, which is found in Google Earth. This is neccessary to link Capital Plan projects to deficiencies identified during the Trail Assessment. This will also improve reporting of project completion.